## Slide 1: Building the Orders API
How one developer and a team of Claude Code agents went from a prompt brief to a tested .NET 10 API in five days
Demo-API repository · 24-29 October 2026
Notes: This deck walks through the process used to create the Demo-API repository: how the plan was made, who (which agents) made each part, how decisions were recorded, and how the code was built, reviewed and demoed. Everything here comes from docs/product, mainly 00-summary.md and notes.md.

## Slide 2: The journey at a glance
Brief
24 Oct
Prompt template with a fixed stack
Plan
24-27 Oct
Six planning phases, each by an advisor agent
Board
27 Oct
168 work items in Azure DevOps
Build
27 Oct
Agents build slices S1a to S4
Review
27 Oct
Fresh-context code and security reviews
Demo
28 Oct
Narrated video of the API in Scalar
68
decisions logged with an ID
30
agent calls by 16 agent types
168
Azure DevOps work items
401
automated tests passing
Notes: Six stages in five days. Planning took most of the calendar time (24-27 October); building, reviewing and the demo were compressed into the last two days because the plan was detailed enough to hand straight to agents.

## Slide 3: It started with a reusable prompt brief
One file: product-brainstorm-template-dotnet10-webapi.md, pasted into Claude Code
First rule: brainstorm first, no application code until the plan is approved
Stack is fixed: Claude may only raise risks in an “Advice” section
13 open questions (order statuses, refresh tokens, customer delete…) answered in the plan
Reusable: swap sections 1-9 for the next product
Fixed stack
.NET 10 Web API
FastEndpoints
Clean Arch + VSA + CQRS
FluentValidation
PostgreSQL 18
Valkey 9.1 cache
EF Core + Dapper
Identity + own JWT
Resilience
Rate limiting
xUnit v3 + Testcontainers
Azure Pipelines
Notes: The brief is a copy-paste prompt template. It names the product, the users, the fixed technology stack and the open questions, and tells Claude to run the product-brainstorm skill. Section 9 of the brief held 13 open questions; their answers are in 00-summary.md.

## Slide 4: Step zero: check versions and licences
A general-purpose agent checked every package with web search before planning. Four choices in the brief changed.
Redis 8
→ Valkey 9.1
Redis 8 is RSALv2 / SSPL / AGPLv3; Valkey is BSD-3 and a drop-in
MediatR
→ FastEndpoints command bus
MediatR is now paid or reciprocal; the bus is MIT and already in the stack
FluentAssertions
→ Shouldly
FluentAssertions v8 uses a non-commercial licence
FastEndpoints.Swagger
→ FastEndpoints.OpenApi + Scalar
Swagger package is deprecated after 10 Nov 2026
Notes: Output: stack-versions-2026-10-24.md. Same approach also led to Microsoft.Extensions.Resilience instead of a direct Polly reference. These checks protect the long-term goal: a reusable dotnet new template that clients can use without licence surprises.

## Slide 5: /product-brainstorm ran the plan phase by phase
1
Concept
Done
2
Requirements
Done
3
Research
Skipped
4
UX design
Skipped
5
UI design
Skipped
6
Architecture
Done
7
Security
Done
8
Delivery
Done
9
Quality
Done
10
Release
Later
11
Operations
Later
Approval gate after every phase
At most five questions per message to the product owner
Each decision logged in 00-summary.md
Advisor agents draft; the main session merges and saves
Notes: The product-brainstorm skill sets the phase order and the gates. Research, UX and UI design were skipped because the product is an API with no UI. The actual order was Concept, Requirements, Architecture, Security, Quality, Delivery. Release and Operations are planned as light phases.

## Slide 6: Concept and requirements set the scope
60
user stories with Given / When / Then
52
endpoints planned
3
callers in the permission matrix
16
review decisions (D1-D16)
Concept
product-strategist + lean-canvas
Purpose: a reusable template for client APIs. North Star: share of endpoints that meet the Definition of Done (target 100%).
Requirements
requirements-analyst, then 3 in parallel
PRD, endpoint list and a permission matrix for Admin, Customer and anonymous, then 60 stories in three files.
Notes: Writing 60 stories surfaced gaps, recorded as decisions D1-D16 in PRD section 16 (for example: reports keep deleted customers and products, self-delete is POST /customers/me/erase, ExecuteUpdate is banned).

## Slide 7: A pre-mortem attacked the plan before design
devils-advocate imagined the project had failed and listed why: 12 failure reasons, 10 decisions (P1-P10).
F1 Scope too big
What goes wrong
52 endpoints × a 9-item Definition of Done for one person
Decision
Hard time-box per slice; cut stretch work first
F2 Never reused
What goes wrong
Patterns tangled with Orders code; no template
Decision
Template extraction is a deliverable (Epic E6)
F3 Flaky stock locking
What goes wrong
Retries on retries in the order transaction
Decision
SELECT … FOR UPDATE in ID order; one retry layer
Notes: Other pre-mortem decisions: personal data is never stored in the audit log (audit is append-only), customer restore moved to stretch, compose runs as Development with generated dev secrets, reviews are done by fresh-context agents, CI is Azure Pipelines. Kill criteria are in pre-mortem.md.

## Slide 8: Architecture: four specialists, then a challenge
solution-architect
C4 diagrams, request flows
dotnet-architect
Solution structure, ADRs
dotnet-data-specialist
Data model, EF Core + Dapper
dotnet-api-designer
Endpoint catalog, auth, limits
Main session merges
Fixed clashes between parallel agents: DB role names, Valkey timeouts, middleware order
devils-advocate review
Verdict: go with changes (R‑1 to R‑5), e.g. split S1 into a walking skeleton and auth
14 ADRs (0001-0014)
17 architecture decisions
5 review changes
Notes: Each specialist had preloaded skills (for example dotnet-clean-architecture, dotnet-ef-core, dotnet-authz). Usage limits stopped these agents twice; they were resumed with SendMessage, not restarted. After the devil's advocate review, dotnet-architect was resumed to apply R-1..R-5 to the documents.

## Slide 9: Security and testing were planned, not bolted on
STRIDE threat model
security-privacy-reviewer → S-D1 to S-D8
Security-stamp check on every request
Same work and time floor on login and register, so accounts can’t be guessed
Compose on localhost only; Valkey needs a password
Supply-chain gates and Renovate in CI
Test pyramid (planned counts)
qa-strategist → Q-D1 to Q-D6
Chart: 
| Integration / API | Unit | Serial | Architecture rules
Planned tests | 350 | 200 | 40 | 20
No automatic retries in CI. Whole suite must run in 5 minutes or less.
Notes: Security decisions are in threat-model.md section 9 and ADR 0014. The test strategy adds a generated authorization matrix (every endpoint tested as Admin, Customer and anonymous), at most three quarantined tests, and coverage as a warning only.

## Slide 10: Thin slices with hard time-boxes
Chart: Time-box per slice (days, upper bound)
| S1a skeleton | S1b auth | S2 customers | S3 orders | S4 reports | Template + ops
Days (upper bound) | 18 | 28 | 20 | 15 | 8 | 9
delivery-planner: Kanban, WIP 1, one story per PR, an Epic per slice
168 work items with 160 parent and 31 dependency links
Preview, then apply: azdo-boards-manager showed every item before anything was created
Commits reference AB#<id> so code links back to the board
Notes: Total planned effort was 83-98 days of one-developer time. When the agent's write call was denied by the auto-mode permission check, the main session created the items through the Azure DevOps REST API with the same token, then verified them. The item IDs are in azdo-map.md.

## Slide 11: Every decision has an ID and a home
Chart: 
| Requirements (D) | Pre-mortem (P) | Architecture (A-D) | Arch review (R) | Security (S-D) | Quality (Q-D) | Delivery (DL-D)
Decisions | 16 | 10 | 17 | 5 | 8 | 6 | 6
68
decisions, each with a date, a reason and a link
00-summary.md is the single log
ADRs explain the why
CLAUDE.md: when code and docs disagree, raise it; never change a decision silently
Notes: Decision IDs make it easy to trace a line of code or a test back to a choice. For example, P4 (no personal data in the audit log) explains why the audit table is append-only and why the app writes the word 'changed' instead of values for personal fields.

## Slide 12: A team of agents turned the plan into code
dotnet-api-designer
51 endpoints in feature folders (Auth, Products, Customers, Orders, Reports, AdminUsers). Release build with 0 warnings.
dotnet-devops-engineer
Chiseled non-root Dockerfile, compose with generated dev secrets, Azure Pipeline with format, vulnerability and secret scans.
dotnet-test-engineer
217 unit, 45 architecture and 134 integration tests. Found and fixed 3 production bugs along the way.
api-collection-engineer
10 .http files with about 320 requests, including 401, 403, BOLA, 412 and 428 cases.
Notes: The build ran on branch feature/build-orders-api. The user asked mid-build to use the existing agents and skills, so the remaining work was handed to agents #22 to #25 in notes.md. The main session fixed integration issues the agents left, such as a missing AddRateLimiter call, then smoke-tested docker compose up.

## Slide 13: Fresh-context reviews found real issues
Chart: Findings by severity
| Code review | Security review
High | 1 | 0
Medium | 5 | 3
Low | 13 | 8
Fixed, with a test for each
Wrong current password never counted toward lockout
Register revealed whether an email already existed
Fake email sender logged reset links in every environment
Concurrency conflicts returned 500 instead of 409
7 findings left open on purpose, each with a written reason.
After fixes: 0 build warnings · format clean · 401 tests pass · 9 of 9 .http files pass against the running stack
Notes: The reviewers (dotnet-code-reviewer and dotnet-security-reviewer) start with no memory of how the code was written and cannot edit files. Their condensed findings and the fix for each are in 07-quality/review-2026-10-27.md, tracked on Azure DevOps story #170.

## Slide 14: Then the API demoed itself
Script
narration.json
Voice-over
edge-tts, en-US Ava
Drive + record
Playwright in Scalar, 1600×900
Edit
FFmpeg mix and encode
Share
Loom, linked in the README
103 s
narrated walkthrough, 1600×900
Health check, login, products, customers and orders, all against the real compose stack. Every step is scripted in docs/product/10-launch/demo, so the video can be re-recorded for the next version.
Notes: The first upload attempts to Loom through the Atlassian MCP server failed; the steps and the failure are recorded in demo-video-steps.md. The final video link is now in the README.

## Slide 15: Guardrails kept the process honest
Approval gates
No code until the plan was approved; no board write without a preview
Read-only reviewers
Reviewers report findings; they never edit the code they judge
Hooks
Blocked risky actions, such as writing a secrets file, instead of working around them
notes.md
Every agent and skill call logged: 30 agent calls so far
CLAUDE.md
Stack, data rules and Definition of Done load into every session
Resume, don’t restart
Agents stopped by usage limits were resumed with their context
Notes: These guardrails matter more than any single agent. Examples from the log: the guard-secrets hook blocked a .env.example file and the agent stopped and reported it; a guard-api-commands hook blocked a command containing the word Production. Later agents were told to stop and report hook blocks rather than find another way.

## Slide 16: What’s next
Template extraction
dotnet new template with SharedKernel, BuildingBlocks, Auth, AdminUsers and Products
Release and operations (light)
Release checklist, health and logging notes, runbook
Close the gaps
Fix the incomplete OpenAPI export (Bug #169), then generate Postman and add a drift check
Name a reuse target
Pick a client project to adopt the template, with its security owner
Plan first.
Decide in writing.
Let fresh eyes review.
Notes: The open questions from 00-summary.md: which client project will reuse the template (needed before S3 per pre-mortem F2), and that project's security owner and compliance needs.